Mars-Analog Scout Rover

Project Plan & Build Schedule

Rodolfo Yanez  |  Mechanical Engineering, University of Arizona

# Mission Goal

Design, build, and field-test a self-righting, dust-tolerant scout rover as a single-semester portfolio project targeting mechanical and aerospace internships in the Mars / space robotics space.

The rover addresses two failure modes that have ended real Mars missions:

- Loss of mobility from chassis inversion. A flipped rover is a dead rover without active recovery. Smaller scout-class rovers cannot rely on the wide, low geometry that protects Curiosity and Perseverance.

- Dust ingress into drivetrain components. Martian regolith is electrostatically charged and abrasive; Spirit's wheel actuators degraded from dust exposure. Most hobby rovers ignore this entirely.

The goal is not to replicate JPL hardware. The goal is to take JPL-class problems, scope them to hobby budget and timeline, and document the engineering decisions made along the way - the part recruiters actually care about.

## Measurable Design Goals

| # | Goal | Target |
| --- | --- | --- |
| 1 | Autonomous obstacle avoidance | No collision over 5-min run |
| 2 | Live camera stream | <500 ms latency, 480p min |
| 3 | Self-right from any inverted orientation | 100% success over 10 trials |
| 4 | Sealed drivetrain | 2+ hrs in desert sand, no degradation |
| 5 | Thermal tolerance | Operate in 95F+ ambient |
| 6 | Battery life | >= 45 min continuous drive |

# Bill of Materials

Phase 1 + Phase 1.5 estimated cost. Final list will be locked in after CAD is complete and motor sizing is confirmed. All electronics sourced from Amazon, Adafruit, or SparkFun - never general hardware stores.

| Subsystem | Component | Source | Cost |
| --- | --- | --- | --- |
| Compute | Raspberry Pi 4 (4GB) | Adafruit | $55 |
| Compute | 32GB microSD card | Amazon | $10 |
| Drive | TT gear motors x4 + wheels | Amazon | $15 |
| Drive | L298N motor driver | Amazon | $8 |
| Drive | Sealed bearings 608ZZ x8 | Amazon | $10 |
| Sensing | HC-SR04 ultrasonic x3 | Amazon | $10 |
| Sensing | Pi Camera Module v2 | Adafruit | $25 |
| Sensing | MPU-6050 IMU | Amazon | $5 |
| Power | 18650 cells x3 + holder | Amazon | $20 |
| Power | TP4056 charger module | Amazon | $5 |
| Power | 5V buck converter | Amazon | $8 |
| Mechanism | MG996R servo (righting arm) | Amazon | $8 |
| Hardware | M3 screws, standoffs, jumpers | Amazon | $30 |
| Hardware | PETG filament | UA printer | $20 |
| TOTAL | Phase 1 + 1.5 estimate |  | ~$229 |

Total project budget: $300 - $500. ~$229 in Phase 1 + 1.5 components leaves headroom for failures (expect to lose 1-2 components as a first-time builder) and Phase 2 GPS hardware.

# Build Schedule (10 Weeks)

Phased plan. Each phase produces a working, demoable milestone - not a half-finished system. The rover drives before it self-rights; it self-rights before it goes to the desert.

| Phase 1: Drive + Perceive | Phase 1.5: Differentiators | Phase 2: Field Testing | Phase 3: Future |
| --- | --- | --- | --- |

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Write README + plan repo |  |  |  |  |  |  |  |  |  |  |
| CAD chassis + righting arm |  |  |  |  |  |  |  |  |  |  |
| CoM + torque calculations |  |  |  |  |  |  |  |  |  |  |
| Order parts |  |  |  |  |  |  |  |  |  |  |
| Wire & breadboard test |  |  |  |  |  |  |  |  |  |  |
| Assemble drive base |  |  |  |  |  |  |  |  |  |  |
| Obstacle avoidance code |  |  |  |  |  |  |  |  |  |  |
| Camera streaming |  |  |  |  |  |  |  |  |  |  |
| Self-righting mechanism |  |  |  |  |  |  |  |  |  |  |
| Sealed drivetrain integration |  |  |  |  |  |  |  |  |  |  |
| IMU + recovery logic |  |  |  |  |  |  |  |  |  |  |
| Field testing (desert) |  |  |  |  |  |  |  |  |  |  |
| Documentation + writeup |  |  |  |  |  |  |  |  |  |  |

## Phase Milestones

Phase 1 (Weeks 1-5) - Drive and perceive

- Chassis CAD complete and 3D printed

- 4-wheel drive functional under remote control

- Ultrasonic obstacle avoidance working

- Raspberry Pi camera streaming over local network

- Milestone: rover drives itself around an indoor course without collisions

Phase 1.5 (Weeks 6-8) - The differentiators

- Self-righting mechanism integrated and tuned

- Sealed drivetrain components installed (labyrinth seals, sealed bearings)

- IMU-triggered recovery sequence working

- Milestone: rover recovers from forced flips in lab conditions

Phase 2 (Weeks 9-10) - Field testing

- Outdoor testing in Sonoran Desert terrain

- Dust exposure protocol: run, disassemble, document wear

- Before/after photos and writeup of drivetrain components

- Milestone: documented test results showing seal performance

Phase 3 (Post-semester) - Future expansion

- GPS waypoint navigation

- Possible sample-collection gripper (Mars Sample Return inspired)

# Known Risks

- First electronics project. Expect to fry 1-2 components from wrong polarity or voltage. Build environment with this in mind; do not solder anything permanent until breadboard tests pass.

- Self-righting mechanism is a single point of failure. If the servo or linkage breaks, recovery fails. Backup plan: test mechanism in isolation before integrating with the rover.

- PETG prints are harder than PLA. First seal housings may need multiple iterations. Build time buffer into the CAD weeks.

- Desert testing is weather and schedule dependent. Phase 2 needs a backup indoor protocol if field tests slip.